## Project tracker
SL # | Topic | Activity | Date | Effort | Status | Remarks
1 | Project plan | Prepare Project plan | 2021-04-13 | 1hr | complete | detailed prepared plan
2 | Database creation | Create Database | 2021-04-13 | 1hr | complete | dowloaded SQLite and understand how the software works
3 |  | Connect with DB client | 2021-04-13 | 2hr | complete | Downloaded database client Dbeaver and contected to database
4 | Load Data and SQL Analysis | Select a public dataset | 2021-04-14 | 1hr | complete | Reused the sample databse available in Dbeaver
5 |  | Do SQL Analysis | 2021-04-15 | 2.5hr | complete | Learned the joins in the dataset and executed the queries.
7 |  | SQL Analytical functions | 2021-04-15 | 3hr | complete | Excected and learnt analytical functions like rank, desc_rank, with. Downloaded github and Uploaded the 1st data set analysis to github.
8 | Building Reports | Connect PBI to DB and pull data | 2021-04-19 | 2hr | completed | Learned powerBi tool and pull the excel sheet dataset to the powerBI
9 |  | Build reports | 2021-04-22 | 4hr | completed | manually build the E-R diagram and relatioship between the tables
10 |  | Build advanced reports | 2021-04-27 | 2hr | completed | understood different graph and explored tooltip, drill down
11 | Prepare Project report | Steps followed
12 |  | Learning: Technical, Management
13 |  | Analysis findings
14 |  | Publish blogpost and update it in LinkedIn
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38