## Project tracker
SL # | Topic | Activity | Date | Effort | Status | Remarks
1 | Project plan | Prepare Project plan | 2021-04-13 | 1hr | complete | detailed prepared plan
2 | Database creation | Create Database | 2021-04-13 | 1hr | complete | dowloaded SQLite and understand how the software works
3 |  | Connect with DB client | 2021-04-13 | 2hr | complete | Downloaded database client Dbeaver and contected to database
4 | Load Data and SQL Analysis | Select a public dataset | 2021-04-14 | 1hr | complete | Reused the sample databse available in Dbeaver
5 |  | Do SQL Analysis | 2021-04-15 | 2.5hr | complete | Learned the joins in the dataset and executed the queries.
7 |  | SQL Analytical functions | 2021-04-15 | 3hr | complete | Excected and learnt analytical functions like rank, desc_rank, with. Downloaded github and Uploaded the 1st data set analysis to github.
8 | Building Reports | Connect PBI to DB and pull data | 2021-04-19 | 2hr | completed | Learned powerBi tool and pull the excel sheet dataset to the powerBI
9 |  | Build reports | 2021-04-22 | 4hr | completed | manually build the E-R diagram and relatioship between the tables
10 |  | Build advanced reports | 2021-04-27 | 2hr | completed | understood different graph and explored tooltip, drill down
11 | Prepare Project report | Steps followed | 2021-04-28 | 1hr | completed
12 |  | Learning: Technical, Management | 2021-04-28 | 2hr | completed
13 |  | Analysis findings | 2021-04-28 | 1hr | completed
14 |  | update it in LinkedIn | 2021-04-28 | 1hr | completed
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38